## Sheet1
Kuiseb Flood damage Year 2000
Gobabeb FLOOD DAMAGES
|  |  | May |  | June |  |  |  | July |  |  |  | August
Description | Estimate Costs | Comments | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
Damage to supply cable | 10000 | 380 volt 200 m | May Week 3: zzzzzzzz
DOROP FLOOD DAMAGES | bar: May Week 3
|  |  | May |  | June |  |  |  | July |  |  |  | August
Description | Estimate Costs | Comments | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
South 11 line (borehole 10,8,13,11,,9,14, and 12)
Pipeline washed away from 8 to 11 to 9 | 150000 | 200mm class 12, 500m | June Week 1: xxxxxxxxxxxxxxxxxxxxxxxxxxxxxx
Electrical cables need to be tested | 20000 |  | June Week 2: xxxxxxx
Electrical cables need to be protected | 50000 |  | June Week 2: xxxxxxxxxxxxxxx
Connector pipe,line 6 and line 11, washed away | 50000 |  | June Week 1: xxxxxxxxxxxxxxx
Pipe and cable to Pump 3 washed away | 40000 |  | June Week 1: xxxxxxxxxxxxxxx
Collector pipeline to High Dune washed away | 600000 | 300mm class 18, 1000m | June Week 3: xxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxx
Total | 910000
Rooibank A
|  |  | May |  | June |  |  |  | July |  |  |  | August
Description | Estimate Costs | Comments | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
Pump 8 - Pipe washed away - repaired | 3000 | 150mm A/C 30 m | May Week 3: zzzzxxxx
Pump 8 - Cable washed away repaired | 10000 | 11KV, 16mm square 40 m | May Week 3: zzzzxxxx
Pump 10a and 10b - Pipe washed away - repaired | 5000 | UPVC 30 m - 110mm | May Week 3: zzzzxxxx
Pump 10a and 10b - Cable washed away | 10000 |  | May Week 3: zzzzxxxx
P1 - Pipeline washed away - repaired | 8000 | 150mm A/C 30 m | May Week 3: zzzzxxxx
P1 - Cable washed away expect more damage | 20000 |  | May Week 3: zzzzxxxx
P2 - Pipeline washed away | 15000 | 300m 150mm A/C class 18 | May Week 3: zzzzxxxxxxxxxxxxx
P2 - Foundation washed away, replace gabions | 15000 |  | June Week 2: xxxxxxxxxxxxxxxxx
Pipeline washed away from pump 7 to the collector line | 5000 | Old galv. steel pipe 100mm | June Week 2: xxxxxxxx
Pipeline washed away from pump 9 to 5 | 30000 | 200mm class 18, 40 m | May Week 3: zzzzzzxxxxxxxxxx
Pump 5 need to be protected | 15000 |  | June Week 2: xxxxxxxx
Pump 5 Electrical Installation and pipe to be protected | 15000 |  | June Week 2: xxxxxxxx
Collective cable to 8,9 and P1 damaged - repaired | 50000 | 11KV, 16mm square 250 m | May Week 3: zzzzzzzz
Protect electrical cable | 100000 |  | June Week 2: xxxxxxxx
Cable damaged at Pump 2 | 8000 | 60 m 380V | May Week 3: zzzzzzzz
Cable damaged at Pump 11 | 5000 |  | June Week 1: xxxxxxxx
Protect all pipes that were exposes but not damaged | 100000 |  | June Week 1: xxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxx
Protect all cables that were exposes but not damaged | 100000 |  | June Week 1: xxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxx
Pipeline washed away close to Rooibank |  | Not to be repaired.
Total | 514000
Rooibank B
|  |  | May |  | June |  |  |  | July |  |  |  | August
Description | Estimate Costs | Comments | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
Pump B1 - Pipeline washed away. | 10000 | 150mm A/C class 18 | June Week 2: xxxxxxxx
Pump B1 - Cable washed away. | 10000 |  | June Week 2: xxxxxxxx
Damage to the installation, borehole full of sand | 15000 | Casing lid open | June Week 2: xxxxxxxx
Damage to pump | 15000 |  | June Week 2: xxxxxxxx
Pump B3 - Transformer washed away | 20000 |  | June Week 2: xxxxxxxx
Electrical cables damaged | 5000 |  | June Week 2: xxxxxxxx
Total | 75000
Swartbank
|  |  | May |  | June |  |  |  | July |  |  |  | August
Description | Estimate Costs | Comments | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
Pipeline washed away to Fehlman | 100000 | 400mm class 18, 2 places | May Week 3: xxxxxxxxxxxxxxxxx; June Week 2: xxxxxxxx
Cable washed away, or damaged to Fehlman | 50000 |  | May Week 3: xxxxxxxxxxxxxxxxx
Load test on cable | 10000 |  | June Week 2: xxxxxxxx
Pipeline washed away from DNA 1 to NA2 | 150000 | 150mm class 18, 300m | June Week 2: xxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxx
Pipeline to collector 2 washed away | 50000 |  | July Week 1: xxxxxxxxxxxxxxxxx
Pipeline washed away NA2 to NA4 | 50000 |  | July Week 2: xxxxxxxxxxxxxxxxx
Pipeline washed away NA4 to collector pipe | 50000 | 50m, 300mm class18 | July Week 3: xxxxxxxxxxxxxxxxx
Pipeline washed away M5 to M165 | 100000 | 300mm class19 | August Week 1: xxxxxxxxxxxxxxxxxxxxxxxxxx
DNA 1 - Transformer and installation washed away | 250000 |  | June Week 2: xxxxxxxxxxxxxxxxxxxxxxxxxx
Overhead elec. Line damaged - NAE1 To DNA 1 | 40000 | 400m | May Week 3: xxxxxxxx
Overhead elec. Line damaged - NA2 to NA4 | 40000 | 400m | May Week 3: xxxxxxxx
Overhead elec. Line damaged - E1 to NAE1 | 40000 | 400m | May Week 3: zzzzzzzz
Overhead elec. Line damaged - LS1 to LS2 | 40000 | 400m | May Week 3: zzzzzzzz
Overhead elec. Line damaged 300m - LS2 to LS3 | 30000 | 300m | May Week 3: xxxxxxxx
Incoming cable damaged - LS2, S6 and M5 | 15000 | 380volt 150m | May Week 4: xxxxxxxx
Overhead elec. Line damaged - LS4 to S6 | 80000 | 800m | June Week 1: ZZZZZZZ
Overhead elec. Line damaged - S6 to S2 | 80000 | 800m | June Week 2: xxxxxxxxxxxxxxxx
Overhead elec. Line damaged - M5 to S6 | 70000 | 700m | June Week 3: xxxxxxxxxxxxxxxxxxxxxxx
Overhead elec. Line damaged main supply M5 to M165 | 90000 | 900m | July Week 1: xxxxxxxxxxxxxxxxxxxxxxxxxx
Protect poles and straighten | 100000 |  | July Week 2: xxxxxxxxxxxxxxxxxxxxxxxxxx
Protect all pipes that were exposes but not damaged | 100000 |  | July Week 4: xxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxx
Total | 1535000
Overhead costs | 100000
TOTAL OF CENTRAL MAINTENANCE | 3144000 |  | May Week 3: zzzzzzzz; May Week 4: Done
Plus 10% unexpected | 314400
Total | 3458400 |  | May Week 3: xxxxxxxx; May Week 4: Programmed